## Weekly Task Tracker
Week | Dates | Team_Member | Task | Hours_Estimated | Status | Notes
1 | Oct 27-Nov 2 | All | Team kickoff meeting + role finalization | 1
|  |  | Get API keys (PubMed, Claude) | 1
|  |  | Setup development environment | 2
|  | Satya | PostgreSQL installation & setup | 3
|  |  | Database schema design (3 tables) | 3
|  |  | Create tables & indexes | 2
|  | Elenta | Setup Biopython environment | 2
|  |  | Build PubMed article fetching function | 3
|  |  | Implement XML parsing for metadata | 2
|  | Rahul | Setup Claude API client | 2
|  |  | Test basic Claude API calls | 2
|  |  | Design initial prompt template | 3
2 | Nov 3-9 | Satya | Test database insert/query operations | 2
|  |  | Build cache lookup functions | 3
|  |  | Implement cache storage logic | 3
|  |  | Create database indexes for performance | 2
|  | Elenta | Pre-seed database: 10 topics × 5 articles | 4
|  |  | Connect PubMed pipeline to database | 3
|  |  | Build citation formatting module | 2
|  | Rahul | Refine prompt with test abstracts | 3
|  |  | Build keyword extraction from questions | 4
|  |  | Test end-to-end: question → Claude → response | 3
3 | Nov 10-16 | Satya | Build performance tracking queries | 3
|  |  | Create analytics for cache hit rate | 3
|  |  | Database optimization & cleanup scripts | 3
|  | Elenta | Integrate PubMed → Database → Claude pipeline | 4
|  |  | Add API failure error handling | 3
|  |  | Implement rate limiting enforcement | 2
|  | Rahul | Build Streamlit basic chat interface | 4
|  |  | Add loading indicators & status messages | 2
|  |  | Optimize PubMed search query generation | 3
4 | Nov 17-23 | Satya | Performance testing & metrics collection | 3
|  |  | Database documentation & schema diagrams | 3
|  |  | Prepare performance slides for presentation | 2
|  | Elenta | Integration testing (20+ test questions) | 4
|  |  | Edge case handling & validation | 3
|  |  | Create setup/installation guide | 2
|  | Rahul | Streamlit UI polish & styling | 3
|  |  | User experience testing with classmates | 2
|  |  | Create README documentation | 3
5 | Nov 24-30 | Satya | Final performance metrics & cost analysis | 2
|  |  | Review & finalize all documentation | 2
|  | Elenta | Final integration testing & bug fixes | 3
|  |  | Verify all citations format correctly | 2
|  | Rahul | Final UI testing & improvements | 2
|  |  | Prepare live demo script | 2
|  | All | Create presentation slides (8-10 slides) | 4
|  | All | Practice presentation (2-3 run-throughs) | 3
|  | All | Record backup demo video | 2
|  | All | Final testing of entire system | 2

## Deliverables & Metrics
Week | Dates | Deliverable | Due_Date | Status | Owner | Link_Location
1 | Oct 27-Nov 2 | Development environment setup | Nov 2 | Not Started | All
1 | Oct 27-Nov 2 | API keys obtained (PubMed + Claude) | Nov 2 | Not Started | All
1 | Oct 27-Nov 2 | Database schema created | Nov 2 | Not Started | Satya
1 | Oct 27-Nov 2 | PubMed API wrapper working | Nov 2 | Not Started | Elenta
1 | Oct 27-Nov 2 | Claude API integration tested | Nov 2 | Not Started | Rahul
2 | Nov 3-9 | Database with 50 PubMed articles | Nov 9 | Not Started | Elenta
2 | Nov 3-9 | Response caching system working | Nov 9 | Not Started | Satya
2 | Nov 3-9 | Prompt template finalized | Nov 9 | Not Started | Rahul
3 | Nov 10-16 | End-to-end pipeline functional | Nov 16 | Not Started | Elenta
3 | Nov 10-16 | Streamlit UI basic version | Nov 16 | Not Started | Rahul
3 | Nov 10-16 | Performance tracking implemented | Nov 16 | Not Started | Satya
4 | Nov 17-23 | 20+ test questions completed | Nov 23 | Not Started | Elenta
4 | Nov 17-23 | Full documentation (README + setup) | Nov 23 | Not Started | Rahul
4 | Nov 17-23 | Database documentation & diagrams | Nov 23 | Not Started | Satya
5 | Nov 24-30 | All testing complete | Nov 30 | Not Started | All
5 | Nov 24-30 | Presentation slides ready | Nov 30 | Not Started | All
5 | Nov 24-30 | Demo video recorded (backup) | Nov 30 | Not Started | All
5 | Dec 1 | FINAL PRESENTATION | Dec 1 | Not Started | All
SUCCESS METRICS
Metric | Target | Actual | Pass_Fail | Notes
Articles cached | 50+
Cache hit rate | 60%+ |  |  | Test with 20+ questions
Avg response time (cached) | < 5 sec
Avg response time (new query) | < 10 sec
Questions tested | 20+
Citation accuracy | 100% |  |  | All responses have proper citations
Claude API cost per query | < $0.02
Total project cost | < $5 |  |  | Track Claude API usage
RISKS & ISSUES
Risk_ID | Risk_Description | Impact | Probability | Mitigation_Strategy | Status | Owner | Date_Identified
R1 | PubMed rate limiting delays data collection | Medium | High | Respect 3 req/sec limit, pre-seed early in Week 2 | Open | Elenta | Oct 27
R2 | Claude API costs exceed $5 budget | Medium | Medium | Aggressive caching, limit to 3 abstracts per query | Open | Rahul | Oct 27
R3 | PostgreSQL setup complexity | Low | Medium | Budget extra time Week 1, have SQLite as backup plan | Open | Satya | Oct 27
R4 | Thanksgiving week availability (Nov 28) | High | High | Complete all core work by Nov 27, only polish after | Open | All | Oct 27
R5 | Team member unavailability | Medium | Medium | Clear task ownership, weekly syncs, GitHub for collaboration | Open | All | Oct 27
R6 | Streamlit learning curve | Low | Low | Start with CLI if behind, Streamlit is enhancement | Open | Rahul | Oct 27
WEEKLY PROGRESS SUMMARY
Week | Dates | Tasks_Planned | Tasks_Completed | Percent_Complete | Key_Achievements | Blockers | Next_Week_Focus
1 | Oct 27-Nov 2 | 12 | 0 | 0% |  |  | Setup foundation
2 | Nov 3-9 | 10 | 0 | 0% |  |  | Integration
3 | Nov 10-16 | 9 | 0 | 0% |  |  | UI & Polish
4 | Nov 17-23 | 9 | 0 | 0% |  |  | Testing & Docs
5 | Nov 24-30 | 10 | 0 | 0% |  |  | Presentation
MEETING LOG
Date | Attendees | Topics_Discussed | Decisions_Made | Action_Items | Next_Meeting
Oct 27 | Satya, Elenta, Rahul | Project kickoff, review scope | Confirmed PostgreSQL, Streamlit, roles | All: Get API keys by Oct 28; Satya: Setup PostgreSQL; Elenta: Setup Biopython; Rahul: Test Claude API | Nov 3